Kathleen Deboer

Assignment 1

Interview a Project Manager

INFOST 490-201

Andrew Neuhaus, husband of a childhood friend of mine, has worked as the Senior Project Manager at Travelport, Inc. for 20 years. Schwalbe's explanation of the closing processes and formalizing acceptance contributed to my understanding about the project lifecycle having a distinct end (Schwalbe, 2018). However, Andrew regularly is assigned a project which has already been in-process and has, in its history, had multiple Project Managers. Therefore, his description of how he set project goals and monitored the project's progress was that there is often a project plan and schedule already in place. When he is given a project, he takes a deductive approach by looking at the project's objective. This verifies the necessity for the project charter and documentation, especially when projects change hands (Schwalbe, 2018). Next, Andrew stated, "I'll review with all Stakeholders to ensure the deliverables are still valid, revise, then re-baseline if necessary."

The tools Andrew uses to monitor progress varied depending on the project's methodology. For example, certain tools like Microsoft Project work very well with waterfall-based projects, where tasks typically follow one another.  Whereas with an Agile approach, he will use a tool more suited for that methodology such as JIRA or Trello, which have better features to allow for release-based projects (development, agile, etc..). Documentation is another tool Andrew uses for checks and balances and points of reference throughout the project lifecycle. Many of which Schwabe also presents as necessary for project success, such as the project charter, ROI, and scope statement (Schwalbe, 2018). Andrew also needs to see the roles and responsibilities, or rather the 'players'. This is all the resources who will be working the project, complete with descriptions of their work on the project. Another key focus for monitoring a project is managing risk. Every project or initiative has some risk involved. Working with the team before and during a project's lifecycle to constantly identify roadblocks and challenges helps Andrew to mitigate any issues before a remediation incident occurs. A final key element to Andrew's methods in project management is testing. Stating that everything needs to be tested before it moves into a production environment. Andrew said, "By having a clear testing plan and execution, ensures that a faulty solution doesn't move into production and that all parties have signed off that the solution is valid and viable."

On a side note, Andrew explained that the requirements document is essential for waterfall-based projects; however, this document doesn't exist with agile projects.

Schwalbe states, regarding the agile approach, that the requirements are kept as a living document that is updated regularly. This is why the agile approach has frequent team checkpoints and collocates team members often (Schwalbe, 2018). Customer satisfaction is transparent with each iteration because they can view a working product. Therefore, Andrew's statement that agile projects do not have a requirements document is in sync with Schwalbe because the requirements constitute the backlog created to determine tasks to be completed.  (Schwalbe, 2018)

When ask how Andrew ensures that his project is on schedule to meet the deadline, his response was that communication is key. This is no surprise to me because Andrew is a very charismatic outgoing person, who wants to meet and talk to everyone he encounters. Andrew explained that at the start of each week, he'll send a communication to any resource who has a task to perform during that week. This way, there are no surprises that a deliverable will arrive unnoticed. He cited three techniques that he uses to manage his schedule:

- Ensure that a good communication plan is set where there is a recurring cadence for meetings with Resources, Stakeholders, and Leadership.

- Add 25% contingency when recording times-to-deliver for most goals.

- Critical path diagrams, a solid architecture diagram, Gantt charts - they're all needed to ensure project success. Report in the manner requested by Leadership.

Andrew's method of providing reports in the manner that Leadership desires correlates with Schwalbe's project quality management and project communications 's methods to satisfy key stakeholders' needs and expectations (Schwalbe, 2018).

Andrew finds his approach to team conflict very effective. For example, if he has a resource behind on a deliverable, he doesn't get angry or escalate to Thamhain and Wilemon's influence of authority, but rather requests the completion time, and includes it highlighted in red in his status report (Schwalbe, 2018). He then alerts the deficient line-of-business owner to be aware that Leadership may have questions about the delay. This seems to me to be a passive way of using his authority by transferring the influence of power up the hierarchy (Schwalbe, 2018). Alternatively, he reflects Blake and Mouton's strategy of handling conflict with confrontation, problem-solving, and collaboration. Andrew directly (confrontation) seeks to learn why it is delayed, he then works to agree on a reasonable goal (problem-solving). Should that fail, Andrew meets with the resource's boss to review the work schedule to see if his project can be re-prioritized (collaboration). If not, then he will record this in his status report.

Andrew overcame a recent challenge during a project to migrate nine lines of reporting tools to the Service Now enterprise suite. He executed with the standard waterfall program and each project manager was assigned a line of business. There was no development cost due to the CTO directive to adapt out-of-the-box solutions offered by Service Now. When the CTO left the company mid-project, it was left without backing from senior leadership. The new leadership changed the directive to tailor the solution rather than enforce the out-of-box. Andrew's challenge was keeping to the schedule since each line of business was scheduled to migrate one after another. His solution was to have requirements recorded for each line of business and target dates set for delivery (waterfall). However, the development for each would be simultaneous and work in separate sprints using the agile method. Next, he shifted back to waterfall for testing and delivery.  By each line of business, development working simultaneously using agile, rather than linearly using waterfall, he was able to keep the original target date for delivery. Andrew's solution is an example of Schwalbe's technique of fast tracking activities in parallel, to manage the schedule. Also, that the agile approach is more concerned with completing tasks and delivery per each iteration (Schwalbe, 2018).

Andrew emphasized communication as key lessons learned from managing projects. Specifically knowing what leadership expects regarding report progress, ensuring all lines of business connected to the project are well informed, and establishing a recurring cadence for Stakeholders. Also, once a project schedule has been set, baselined, and distributed, identify resources as soon as is feasible and reserve their time to mitigate resource delays.

In conclusion, I learned that projects can have a history, which emphasizes the importance of documentation. I learned that Project Managers, like Andrew, do regularly use Schwalbe's Theories of Project Management Process Groups and the methods, techniques, and tools to manage successful delivery.

Appendix A

Interview Questions

Andrew Neuhaus

Who do you work for?      Position?     Years experience as a Project Manager?

1.) How do you set project goals and monitor the progress? Include any pertinent details about tools/software used or tips on how you keep your finger on the pulse of a project. (e.g. software (Microsoft Project…, SWOT, WBS, scope verification techniques…).

2.) How do you deal with team conflict and/or politics? Which approach to conflict resolution do you use: collaborating, competing, compromising, avoiding, accommodating, or a combination? Do you primarily fall into one of Thamhain and Wilemon's influence and power categories? [Authority (influence by hierarchy), assignment (influence of later work assignments), budget (use of discretionary funds), promotion, money, penalty, work challenge, expertise, or friendship?]

3.) How do you ensure that your project is on schedule to meet the deadline? Or how do you manage the triple constraint? Mention any tools and tips such as project network diagrams, critical path analysis, crashing, fast tracking and Gantt charts, communication techniques...

4.) Please mention a recent challenge you encountered and how you overcame it. Or, what is the most common challenge, e.g. satisfying customer/stakeholder, team personalities, budget…?

5.) What are some key lessons learned from project failure or near failure? Or, perhaps mention a project that experienced creep or went over in schedule or cost and was therefore dropped. Would you have done something differently? If you do not have an example, please mention what goes into avoiding risky projects and choosing the right ones.

Thank you so much for taking time to answer these!

Regards,

Kathleen

Resource

Schwalbe, K. (2018). Information Technology Project Management, Ninth Edition. Course Technology-Cengage Learning.